## Risk Register
Risk Register
Identity |  | Analyze |  |  |  | Plan Response |  | Monitor and Control
ID | Description | Category | Probability | Estimated Impact | Add. Workload (days) | Status | Mitigation action/ counter-measures | Overall Costs
1 | Platform downtime during exams | Technical | 25% | 90% | 12 | Response Planned | Load balancing, scaling infrastructure | 4500
2 | Planning mistakes | Schedule | 30% | 70% | 15 | Occurred (Issue) | Agile review cycles, sprint retrospectives | 3000
3 | Data leaks | Legal/Security | 10% | 95% | 15 | Monitoring | Encryption, access controls | 7000
4 | Poor user experience | UX/Technical | 20% | 60% | 8 | Monitoring | Usability testing, responsive design | 2200
5 | Inaccessible UI for certain devices | External/Technical | 15% | 50% | 6 | Monitoring | Cross-device testing, responsive framework | 1800
6 | Lack of student engagement | Quality | 35% | 70% | 14 | Response Planned | Gamification, interactive content | 5500
7 | Difficulty providing funding | Financial/Resource | 20% | 60% | 7 | Monitoring | Budget planning, partnership outreach | 1000
8 | App crash during peak times | Technical | 15% | 80% | 9 | Occcured (Issue) | Performance profiling, crash reporting | 2800
9 | Misalignment of platform features with actual curriculum | Strategic/Content | 10% | 65% | 10 | Monitoring | Curriculum mapping, stakeholder alignment | 3500
10 | Language barriers amomg international students | UX/Resource | 20% | 40% | 7 | Response Planned | Localization, multilingual support | 2200
11 | Lack of cybersecurity awareness among users | Social/Security | 30% | 55% | 5 | Response Planned | Security training, pop-up hints | 900
12 | Integration issues with existing systems | Technical/Operational | 20% | 70% | 15 | Response Planned | Modular API architecture, pilot testing | 6000
13 | Lack of faculty support | Organizational | 25% | 60% | 8 | Response Planned | Faculty onboarding,feedback involvement | 2400
14 | High data usage | Technical/UX | 10% | 35% | 4 | Monitoring | Data compression,offline options | 1300
15 | Unauthorized plagiarism | Legal/Ethics | 15% | 50% | 6 | Monitoring | Plagiarism detection tools, | 1500
16 | Low user interest due to already existing apps | Competitive/UX | 20% | 60% | 7 | Response Planned | Highlighting unique value, targeted features | 2000
17 | Regulatory changes (e.g. digital standards, law) | Legal/Strategic | 5% | 85% | 10 | Monitoring | Ongoing policy review, flexible platform design | 3800
18 | Resistance from faculty to use the system | Social/Organizational | 20% | 50% | 6 | Response Planned | Change management, incentives | 1800
19 | Loss of key development staff | Resource | 10% | 55% | 7 | Monitoring | Cross-training,documentation,backups | 2200
20 | Delays due to unclear scope | Schedule | 30% | 65% | 8 | Occurred (Issue) | Clear backlog, user stories | 2700