## Risk Register
Risk Register
Identity |  | Analyze | Plan Response
ID | Description | Category | Status | Mitigation action/ counter-measures
1 | Platform downtime during exams | Technical | Response Planned | Load balancing, scaling infrastructure
2 | Planning mistakes | Schedule | Occurred (Issue) | Agile review cycles, sprint retrospectives
3 | Data leaks | Legal/Security | Monitoring | Encryption, access controls
4 | Poor user experience | UX/Technical | Monitoring | Usability testing, responsive design
5 | Inaccessible UI for certain devices | External/Technical | Monitoring | Cross-device testing, responsive framework
6 | Lack of student engagement | Quality | Response Planned | Gamification, interactive content
7 | Difficulty providing funding | Financial/Resource | Monitoring | Budget planning, partnership outreach
8 | App crash during peak times | Technical | Occcured (Issue) | Performance profiling, crash reporting
9 | Misalignment of platform features with actual curriculum | Strategic/Content | Monitoring | Curriculum mapping, stakeholder alignment
10 | Language barriers amomg international students | UX/Resource | Response Planned | Localization, multilingual support
11 | Lack of cybersecurity awareness among users | Social/Security | Response Planned | Security training, pop-up hints
12 | Integration issues with existing systems | Technical/Operational | Response Planned | Modular API architecture, pilot testing
13 | Lack of faculty support | Organizational | Response Planned | Faculty onboarding,feedback involvement
14 | High data usage | Technical/UX | Monitoring | Data compression,offline options
15 | Unauthorized plagiarism | Legal/Ethics | Monitoring | Plagiarism detection tools,
16 | Low user interest due to already existing apps | Competitive/UX | Response Planned | Highlighting unique value, targeted features
17 | Regulatory changes (e.g. digital standards, law) | Legal/Strategic | Monitoring | Ongoing policy review, flexible platform design
18 | Resistance from faculty to use the system | Social/Organizational | Response Planned | Change management, incentives
19 | Loss of key development staff | Resource | Monitoring | Cross-training,documentation,backups
20 | Delays due to unclear scope | Schedule | Occurred (Issue) | Clear backlog, user stories