## Activity of Estimation
Task | Expected Duration | σ² | a | m | b
Educational Platform
1 Initiation & Planing
1.1 Kick of Meeting | 1.1667 | 0.027778 | 1 | 1 | 2
1.2 Stakeholder Identification | 2 | 0.11111 | 1 | 2 | 3
1.3 Define Project Scope & Objectives | 3 | 0.11111 | 2 | 3 | 4
1.4 Develop Project Charter | 3 | 0.11111 | 2 | 3 | 4
1.5 Initial Risk Assesment | 3 | 0.11111 | 2 | 3 | 4
2 Requirements Analysis
2.1 Conduct Stakeholder Interviews | 1.1667 | 0.027778 | 1 | 1 | 2
2.2 Define Functional Requiremnets | 5 | 0.11111 | 4 | 5 | 6
2.3 Validate Requirements | 3 | 0.11111 | 2 | 3 | 4
3 System Design
3.1 Design Rchitecture System (Backend, Frontend) | 4 | 0.11111 | 3 | 4 | 5
3.2 Database Design | 3 | 0.11111 | 2 | 3 | 4
3.3 UI/UX Design | 3 | 0.11111 | 2 | 3 | 4
3.4 Design Review | 2 | 0.11111 | 1 | 2 | 3
4 Development
4.1 Sprint 1
4.1.1 Set Up Dev Envrionment | 3 | 0.11111 | 2 | 3 | 4
4.1.2 Implement Student Registration | 5 | 0.11111 | 4 | 5 | 6
4.1.3 Setup Role-based Dashbord Views | 3 | 0.11111 | 2 | 3 | 4
4.1.4 Build Profile Management (Student/Teacher/Admin) | 3 | 0.11111 | 2 | 3 | 4
4.1.5 Add Password Reset & Email Verification Workflow | 4 | 0.11111 | 3 | 4 | 5
4.1.6 Create Session Timeout & Logout Logic | 3 | 0.11111 | 2 | 3 | 4
4.1.7 Develop Course Management | 10 | 0.44444 | 8 | 10 | 12
4.1.8 Course Draft/Publish Toggle | 3 | 0.11111 | 2 | 3 | 4
4.1.9 Build Instructor Course Overview Page | 5 | 0.11111 | 4 | 5 | 6
4.1.10 Add Tags & Search Fulters for Course Catalog | 3 | 0.11111 | 2 | 3 | 4
4.1.11 Implement Course Enrollment Workflow | 6 | 0.11111 | 5 | 6 | 7
4.1.12 Add Student Course Overview / My Schedule | 5 | 0.11111 | 4 | 5 | 6
4.2 Sprint 2
4.2.1 Develop Learning Material Module | 12 | 1 | 9 | 12 | 15
4.2.2 Implement Acces Control for Materials | 5 | 0.11111 | 4 | 5 | 6
4.2.3 Add Media Uploud | 2 | 0.11111 | 1 | 2 | 3
4.2.4 Add Restriction for Maximum MB of Media Uploud | 2 | 0.11111 | 1 | 2 | 3
4.2.5 Add File Storage System | 5 | 0.11111 | 4 | 5 | 6
4.2.6 Add Function to Set Submission Period | 2 | 0.11111 | 1 | 2 | 3
4.2.7 Add Media Download | 2 | 0.11111 | 1 | 2 | 3
4.2.8 Develop Waitlist & Notification System | 4 | 0.11111 | 3 | 4 | 5
4.2.9 Add Reminder & Notification Settings | 4 | 0.11111 | 3 | 4 | 5
4.2.10 Add Schedule & Calendar Sync | 4 | 0.11111 | 3 | 4 | 5
4.3 Sprint 3
4.3.1 Develop Exam Module | 9 | 0.44444 | 7 | 9 | 11
4.3.2 Quiz/Assesment Generator | 4 | 0.11111 | 3 | 4 | 5
4.3.3 Auto-Grading for Multiple Choice | 2 | 0.11111 | 1 | 2 | 3
4.3.4 Implement Progress Tracking | 2 | 0.11111 | 1 | 2 | 3
4.3.5 Add Function to Calculate Average Course Grade | 1.1667 | 0.027778 | 1 | 1 | 2
4.3.6 Add Exam Timer & Auto-Submit | 1.1667 | 0.027778 | 1 | 1 | 2
4.3.7 Teacher Grading Interface | 3 | 0.11111 | 2 | 3 | 4
4.3.8 Notification for Teacher for Late Submissions | 2 | 0.11111 | 1 | 2 | 3
4.3.9 Export Function for Exam Results | 1.1667 | 0.027778 | 1 | 1 | 2
4.3.10 Export Function for Submissions | 2 | 0.11111 | 1 | 2 | 3
4.3.11 Add Feedback Function for Students for Courses | 2 | 0.11111 | 1 | 2 | 3
4.3.12 Add Feedabck Function for Teachers for Submissions | 1.1667 | 0.027778 | 1 | 1 | 2
4.4 Sprint 4
4.4.1 Develop CommunicationTools | 4 | 0.11111 | 3 | 4 | 5
4.4.2 Implement Messaging System | 4 | 0.11111 | 3 | 4 | 5
4.4.3 Forum / Q&A Report | 2 | 0.11111 | 1 | 2 | 3
4.4.4 Admin Panel | 2 | 0.11111 | 1 | 2 | 3
4.4.5 Dashbord with KPI's | 1.1667 | 0.027778 | 1 | 1 | 2
4.4.6 Exports of Reports | 1.1667 | 0.027778 | 1 | 1 | 2
4.4.7 Add Terms of Service & Privacy Consent Flow | 2 | 0.11111 | 1 | 2 | 3
4.4.8 Add Multi-Language Support | 2 | 0.11111 | 1 | 2 | 3
4.4.9 Add Function to Report Inappropriate Content | 2 | 0.11111 | 1 | 2 | 3
4.4.10 Integrate All Modules | 6 | 0.44444 | 4 | 6 | 8
4.5 Sprint 5
4.5.1 Implement Responsive Login/ Registration Page | 2 | 0.11111 | 1 | 2 | 3
4.5.2 Implement Role-based Navigation Menu (Student/Teacher/Admin) | 4 | 0.11111 | 3 | 4 | 5
4.5.3 Build Resuable Form Components (Inputs, Dropdowns, Validation) | 4 | 0.11111 | 3 | 4 | 5
4.5.4 Add User Feedback (Toast Notification, Loading Spinners) | 2 | 0.11111 | 1 | 2 | 3
4.5.5 Implement Course Detail View (Description, Dates, Instructor) | 2 | 0.11111 | 1 | 2 | 3
4.5.6 Add real-time exam timer with warning indicators | 2 | 0.11111 | 1 | 2 | 3
4.5.7 Enable autosave & resume UI for ongoing assessments | 2 | 0.11111 | 1 | 2 | 3
4.5.8 Display exam results & performance charts (per question/topic) | 3 | 0.11111 | 2 | 3 | 4
4.5.9 Build chat interface (with thread, search, and roles) | 2 | 0.11111 | 1 | 2 | 3
4.5.10 Implement notification center (announcements, alerts) | 2 | 0.11111 | 1 | 2 | 3
4.5.11 Add mobile responsiveness (media queries, flex/grid adjustments) | 2 | 0.11111 | 1 | 2 | 3
4.5.12 Implement dark/light mode toggle | 2 | 0.11111 | 1 | 2 | 3
4.5.13 Apply accessibility improvements (ARIA, tab nav, contrast checks) | 4 | 0.11111 | 3 | 4 | 5
5 Testing
5.1 Write Test Plans & Cases | 3 | 0.11111 | 2 | 3 | 4
5.2 Conduct Unit Testing | 4 | 0.11111 | 3 | 4 | 5
5.3 Conduct Integration Testing | 4 | 0.11111 | 3 | 4 | 5
5.4 Perform Load & Stress Testing | 3 | 0.11111 | 2 | 3 | 4
5.5 Conduct Cross-Browser & Device Testing | 4 | 0.11111 | 3 | 4 | 5
5.6 Conduct User Acceptance Testing (UAT) | 4 | 0.11111 | 3 | 4 | 5
5.7 Prepare Final Test Summary Report | 2 | 0.11111 | 1 | 2 | 3
6 Deployment & Rollout
6.1 Set Up Rollback Plan in Case of Deployment Failure | 5 | 0.11111 | 4 | 5 | 6
6.2 Prepare Production Environment | 2 | 0.11111 | 1 | 2 | 3
6.3 Initial Deployment (Pilot) | 3 | 0.11111 | 2 | 3 | 4
6.4 Gather Pilot Feedback & Fix Bugs | 3 | 0.11111 | 2 | 3 | 4
6.5 Notify Stakeholders & Users About Go-Live | 2 | 0.11111 | 1 | 2 | 3
6.6 Full Deployment (Go-Live) | 2 | 0.11111 | 1 | 2 | 3
7 Training & Documentation
7.1 Write User Manuals | 3 | 0.11111 | 2 | 3 | 4
7.2 Record Tutorial Videos for Key Features | 9 | 0.44444 | 7 | 9 | 11
7.3 Prepare Training Materials | 3 | 0.11111 | 2 | 3 | 4
7.4 Conduct Training Sessions | 4 | 0.11111 | 3 | 4 | 5
8. Maintenance & Evaluation
8.1 Set Up Support & Monitoring | 2 | 0.11111 | 1 | 2 | 3
8.2 Review System Logs & Anomaly Reports Regularly | 3 | 0.11111 | 2 | 3 | 4
8.3 Collect User Feedback | 5 | 0.11111 | 4 | 5 | 6
8.4 Create Evaluation Report (User Stats, Issues, Recommendations) | 3 | 0.11111 | 2 | 3 | 4
8.5 Organize Evaluation Meeting with Key Stakeholders | 2 | 0.11111 | 1 | 2 | 3
∑ | 293.3333 | 11.6667 | 203 | 292 | 389
Probability of project duration
Desired project duration | D | 300 | days
Length of the critical path | μ | 293.3333 | days
Sum of the single variances | ∑σ² | 11.6667
probability that project will be completed in: |  | 300 | days is: | 0,716 (0,571428571428579) | Z= | 71.61%
With a probability of 95% how long will be the duration of the project?
Length of the critical path | μ | 293.3333
Sum of the single variances | ∑σ² | 11.6667
| x | 1.65
With the probability of: | 95% = 1,65 | … the duration of the project will be: |  |  | D = | 312,583 days
)
𝑍=((𝐷−𝜇)/(∑𝜎²))
𝐷=𝜇+∑𝜎²∗𝑥