## Stakeholder Analysis
Stakeholder | Impact of/on change | Gap in support |  | Concerns, issues, resistance | Interest, wins | Influence by | Involvement strategy | Communication channel | What do we need to communicate to the stakeholder? | Who will be in charge of communicating to the stakeholder?
|  | Current mind-set | Support needed
Name, role | High medium low | Resistant Neutral Accept Supportive Committed | Neutral Accept Supportive Committed | - | - | Who can persuade the stake-holder? | What, how, when and who? | E-mail, PDF document on the intranet, Information events, Personal, telephone, Jour fixe, Project repository | Project status/progress, Project contract, Expectations of key stakeholders, Stakeholder analysis, Risk analysis, Status of tasks / work packages, Project closure, project evaluation | -
Project Sponsor: University Management | High | supportive | committed | budget, timeline | project success, modern image | university president, IT strategy board | regular steering meetings, updates | email, steering committee | project goals, timeline, progress | project manager
Teachers: Professors / Lecturers | High | neutral | supportive | additional workload, more streams for contact (chaotic) | simplified course management | department heads | workshops/trainings for usage, feedback | email, workshops, internal platform for announcements | functionality, expected involvement | project manager, department coordinators (, university president)
Students: primary users | High | supportive | committed | usability, functionality, data privacy | better access to material, better communication with teachers | student council | surveys, beta testing, feedback | email, platform notices, feedback forms | benefits, data usage, participation | project communication team
IT department | Medium | supportive | committed | system integration, maintenance load | efficient platform support | project manager | technical meetngs, documentation | tech meetings, internal documentation | system requirements, integration details | technical project lead
Administrative staff: examination office | Medium | neutral | supportive | possible workflow changes, exam handling (registrations etc.) | streamlined admin processes | head of administration | inclusion in planning, workshops/training for usage | email, meetings, memos | changes in workflow, training needs | project manager
Data protection officer | Medium | resistant | supportive | legal compliance with data protection standards (data handling) | compliance with data privacy laws | university legal council | legal review sessions | formal documentation, legal memos | compliance strategy, data handling policy | legal advisor